## Slide 1: Credit Architecture Project Phase 2 Discussion on End-to-End Process Section B – Supplementary Deck

## Slide 2: Contents
Reference Taxonomy for Credit Process
Level 1 Process Maps
  “As-Is” (Presented at OBEYA Jun’14)
  “To-Be” (Presented at 28 Aug’15 CEO Review)
Level 2 Activities (Singapore)
Use Cases
FTE and Benefit Estimates
Phase 2 Governance, Project Plan & Resourcing
Technology Options

## Slide 3: 1. Reference Taxonomy for Credit Process

## Slide 4: Reference taxonomy for Credit Process
Level 0 – 10-Step Credit Process
Level 1 – The next level of detailed processes mapped out in OBEYA and subsequent workshops
Onboard a new group of borrowers
A
A1. Identify the borrowers [I]
A2. Create a new group record [I]
A3. Create new borrower records [I]
A4. Undertake respective KYC process [I]
…
Level 2 – Activity Analysis
I, II, III …
1.01, 1.02, 1.03 …
#1, #2, #3 …
A1, B2, J3…
Use Cases
Taxonomy
E2E Credit Processes

## Slide 5: 2a. Level 1 Process Maps – “As-Is”
Presented at OBEYA Jun’14

## Slide 6: Level 1 Process Maps – “As-Is” (1/ 7)
Note:
Activities above need not occur in sequence as numbered. As indicated by the RM / CRMs, most activities within the stage can happen concurrently
Journey 1.05: Impact on portfolio management
I. Client Targeting
1.01
Check if prospect is within Target Market (Industry and Country) and any non-compliance with core policies
Engage Industry group where applicable
1.02
Check if it’s existing client or EG through AOS.
For Existing Clients, discuss with GRM / LRM if account is active or dormant. Confirmed Dormant, then Initiate tagging/retagging
1.03
For new client- create prospect in AOS
1.04
Determine ultimate parent + engage GRM (+IBG country head)
1.05
Initiate tagging indicators and input key fields
-DBS code
-industry code
-GPIN,GCIN, DOA, EG, TPG etc
1.06
Collect client info (preliminary KYC, Org Charts, Financials etc...) and commence KYC
1.07
Engage Client to understand financial needs
1.08 Input or Update Call Notes (Call Report)
1.09
Engage Product groups (where applicable) and Credit
1.10
Commence discussion with GRM / LRM, GCRM, LCRM on global limits, support framework and workflow (routing)
1.11
Conduct in-principle discussion with RM on pre-approval matters on key credit parameters and structure
AOS
(3G in INDO)
Relationship Manager
Credit Control Unit
Credit Risk Manager
Systems
Notes: Reconcile back the pain points to the activities
Using the same chart for Client Targeting

## Slide 7: Level 1 Process Maps – “As-Is” (2/ 7)
Note:
Activities above need not occur in sequence as numbered. As indicated by the RM / CRMs, most activities within the stage can happen concurrently
RM activities may vary depending on whether it is an credit on-boarding of new or existing client
II. Credit Origination
2.01
Prepare Term sheet
2.02
Prepare MRA and perform financial spreads
2.03
Perform internal Credit Rating process (generation of ACRR)
2.04
Obtain & Update funding and LP allocation for pricing
2.05
Perform country risk assessment and earmarking of necessary limits
2.06
Create facility structure in OSCA
2.07
Input pricing and perform ROE computation
2.08
Aggregate and obtain total group exposure
2.09
Economic capital, relationship cap (R-Cap)
2.10
Establish DOA and determine approving authority (sign off required)
2.11
Check against credit policies for any exception handling procedures required (e.g.. if structure is lending to Hold Co. –> ECRM approval required)
2.12
Ensure compliance of TM (e.g.. determination if parental support is available for structure) and perform assessment on RAC
2.13
Escalations (if required) in any of Policy requirements (e.g.. special attention credits)
OSCA
MRA
2.15
Conduct discussion on term sheet
Note: Depth of discussion may vary depending if client is new or there is existing relationship with the group
2.14
Perform client due diligence (KYC)
KYC
Relationship Manager
Credit Control Unit
Credit Risk Manager
Systems

## Slide 8: Level 1 Process Maps – “As-Is” (3/ 7)
Note:
Activities above need not occur in sequence as numbered. As indicated by the RM / CRMs, most activities within the stage can happen concurrently
OSCA workflow is implemented in India, China, Hong Kong and Taiwan
III. Underwriting
3.01
Complete all sections of credit memo (e.g. CF projection, relevant attachments)
3.02
Review of Memo by IBG Segment Head, GRM and / or IRM (where applicable) and obtain support
3.03
Submit credit memo to Credit Approving Authority (LCRM /GCRM /GrCC)
3.04
Review and approve CRR/ACRR and review prospects in credit memo
3.05
Approve ACRR
3.06
Provide Credit Decision
3.07
Where applicable, cases to be routed to Board
3.08
Answer queries by Board
3.09 Obtain Credit Decision
OSCA
Relationship Manager
Credit Control Unit
Credit Risk Manager
Systems

## Slide 9: Level 1 Process Maps – “As-Is” (4/ 7)
Note:
Activities above need not occur in sequence as numbered. As indicated by the RM / CRMs, most activities within the stage can happen concurrently
IV. LO Issuance
4.01
Prepare letter of offer
4.03
Initiate legal documentation. Appointment of lawyers (where collateral are required)
4.04
Negotiate, credit approval for deviations (Docs / ISDA)
4.08
Approve variations / revisions / deviations of standard terms and conditions
4.05
Seek clearance from legal (internal legal counsel or external legal counsel requires additional approval by internal legal after again)
4.06
Seek approval from CCG
4.07
Additional KYC - if related party requires exceptional Approval (i.e. PEP)
4.10
CSFA assessment-T&M
4.02
Check letter of offer against approved terms
KYC
CFSA
4.09
Send appointment letter to external lawyer and ensure documents are aligned with approve terms
Relationship Manager
Credit Control Unit
Credit Risk Manager
Systems

## Slide 10: Level 1 Process Maps – “As-Is” (5/ 7)
Note:
Activities above need not occur in sequence as numbered. As indicated by the RM / CRMs, most activities within the stage can happen concurrently
VI. Facility Onboarding
6.01
Signoff final doc by client
6.02
Approve waivers, deferrals for conditions precedent with credit impact according to DOA
6.04
Prepare activation form
6.03
Submit all docs + confirm CP to CCU for activation
6.05
Check documents and compliance of CPs
6.06
Perform limit activation
6.07
Upload covenants, terms for tracking
Finacle (Loans), MLC/ Murex (Derivatives), TZ (FX), IMEX/ FactorPro (Trade)
Relationship Manager
Credit Control Unit
Credit Risk Manager
Systems

## Slide 11: Level 1 Process Maps – “As-Is” (6/ 7)
Note:
Activities above need not occur in sequence as numbered. As indicated by the RM / CRMs, most activities within the stage can happen concurrently
VII. Facility Utilization
7.01
Submit requests for transaction deviations, excesses
7.04
Ensure Compliance with conditions precedent, including formal valuation reports
7.02
Ad hoc trade highlights – Obtain blanket approval
7.05
Disbursement: Activation of additional limits
7.03
To review request and either approve / reject request
Relationship Manager
Credit Control Unit
Credit Risk Manager
Systems

## Slide 12: Level 1 Process Maps – “As-Is” (7/ 7)
Note:
Activities above need not occur in sequence as numbered. As indicated by the RM / CRMs, most activities within the stage can happen concurrently
VIII. Risk Monitoring
8.01
Prepare Group Review; interim + annual review (timely submission, satisfactory quality)
8.02
Initiate periodic valuation of collateral (in accordance to guidelines)
8.04
Put up PRO-AM forms , assess impact and categorize (Red, Amber, Green or Weak) where applicable. Provide regular updates on such cases at different forums
8.03
CCG to Approve Group Reviews + Risk Ratings
8.05
Monitor covenants
8.06
Tag debit referrals only if required for monitoring or control of utilization
8.07
Attend and present weak + Watchlist cases at various forms (e.g.. Location Watchlist, NPA Meeting, Board Exco and Risk Exco)
8.08
ICAAP + MAS stress test (conducted manually upon request)
8.09
Confirm results of stress testing
8.10
Conduct Portfolio Review of own accounts
STAR
8.11
Perform periodic valuation of collateral (in accordance to guidelines)
Relationship Manager
Credit Control Unit
Credit Risk Manager
Systems

## Slide 13: 2b. Level 1 Process Maps – “To-Be”
Presented at 28 Aug’15 CEO Review

## Slide 14: Level 1 Process Maps – “To-Be” (1/ 11)
1 Activities may not occur in the numbered sequence. Activities can be performed in parallel and by different persons.
2 e.g. ACRA, S&P, Bloomberg, company websites and where feasible even hard copies (e.g. OCR for Financials)
3 Available on mobile devices
4 In some locations e.g. China, fraud verification may be conducted at a later stage: prior to credit approval
New capability
Involves personal interaction
Existing capability enhanced
I. Client Targeting1
1.02
Check if it is part of the Leads Management database (3rd party). If so, source available data elements.
1.01
Check if it is an existing client and/ or EG/ DOA through AOS
1.03
For new client, create a GCIN lead
1.05
Initiate tagging (Owner, Segment etc.) and input key fields such as (DBSIC, Constitution Code, Country of Incorporation etc.)2
Create new DOA group, if necessary. Replicate into EG, TPG.
Determine ultimate parent along with data from external/public sources2
1.08
Collect Client info (preliminary KYC, Org Charts, Financials, external ratings etc...) and commence KYC, sourcing as much data from external/ public sources2
1.07
Engage Client to understand financial needs. Use analytical tools3 e.g.. Working Capital App, retrieve products for similar customer(s), simulate indicative pricing
1.09 Input or Update Call Notes (Call Report), including photographs e.g.. factory, equipment
1.10
Engage Product groups (where applicable), Industry group, Credit
1.11
Commence discussion with GRM/ LRM/ IRM, GCRM/ LCRM on global limits, support framework and routing
1.12
Conduct in-principle discussion with RM on pre-approval matters on key credit parameters and structure
RM/ CSO/ CAT/ ARM
CRM
Systems
Proposed e2e Credit Workbench
1.06
Screen the prospect for compliance with TMRAC (Industry and Country), core policies and negative history (e.g.. previous rejects), adverse news, known/potential fraud4
1.04
For Existing Clients, discuss with GRM / LRM if account is active or dormant. If dormant, then Initiate tagging/retagging. Else, engage the GRM (+IBG country head)

## Slide 15: Level 1 Process Maps – “To-Be” (2/ 11)
1 Activities may not occur in the numbered sequence. Activities can be performed in parallel and by different persons.
2 Capability to prepare the Term sheet offline and import it into the workbench at a later stage
3 Potentially source the information directly from 3rd parties e.g. Fintechs such as AMP
II. Credit Origination1
RM/ CSO/ CAT/ ARM
CRM
Systems
Proposed e2e Credit Workbench
2.04
When needed, generate the preliminary Term sheet2 for client discussion
2.01
Complete the financial spreading
2.02
Enrich inputs required for the internal Credit Rating
2.05
Source COF and LP for pricing
2.07
Generate the facility country risk and earmark necessary limits
2.03
Set-up3 the facility (limits), collateral, covenant, structuring) & input the pricing; including Relationship Cap (R-CAP), Global Group Limits (“Top-Down” approach)
2.06
Generate the ACRR, FRR, ROE results
2.09
Generate Total Group Exposure, R-Cap, Global Borrower Limits, Economic Capital
2.12
Generate DOA to determine the approving authority and the required routing which will be fully rule based
2.11
Check against policies for exception handling procedures required (e.g.. if structure is lending to Hold Co. –> ECRM approval required)
Escalate (if required) in any of policy requirements (e.g.. special attention credits)
2.10
Verify compliance of TM (e.g.. determination if parental support is available for structure) and perform assessment on RAC
2.14
Enrich information for client due diligence (KYC)
Perform CSFA
2.15
Conduct discussion on term sheet (where needed)
2.08
Complete all sections of credit memo (e.g.. CF projection, relevant attachments)
2.13
Review of Memo by IBG Segment Head, GRM and/ or IRM (where applicable) and obtain support
New capability
Involves personal interaction
Existing capability enhanced

## Slide 16: Level 1 Process Maps – “To-Be” (3/ 11)
1 Activities may not occur in the numbered sequence. Activities can be performed in parallel and by different persons.
2 Actual approval/ rejection should be performed on the system, along with minimal inputs e.g. approval comments, rework reasons
III. Underwriting1
RM/ CSO/ CAT/ ARM
CRM
Systems2
Proposed e2e Credit Workbench
3.02
Review the credit proposal and rework/ approve/ reject it, including all credit approved data e.g.. ACRR, DOA Grouping2, 3
3.01
Submit credit memo to Credit Approving Authority2 3
Follow a streamlined routing process for GrCC & Board Ex-Co approvals
New capability
Involves personal interaction
Existing capability enhanced

## Slide 17: Level 1 Process Maps – “To-Be” (4/ 11)
1 Activities may not occur in the numbered sequence. Activities can be performed in parallel and by different persons.
2 Currently, several segment/ country level variants exist e.g. BSU does LO only for SME, CCU checks LO only for SG IBG1/2
3 Country/Segment level differences could exist on account of staffing differences e.g. lack of BSU in India
IV. LO Issuance1
RM/ CSO/ CAT/ ARM/ BSU
CRM
Systems2
Proposed e2e Credit Workbench
4.01
Generate digitally signed Letter of Offer/Facility Agreement2
4.02
Negotiate with customers, including legal documentation (engage relevant product partners)
4.03
Obtain Credit approval for deviations and seek Legal clearance (Docs / ISDA)
4.06
Approve/ Reject variations/ revisions / deviations of terms and conditions
4.04
Additional KYC - if related party requires exceptional Approval (e.g.. PEP)
4.08
Appointment of lawyers2, 3
4.07
Ensure that the LOs & other internal documents are aligned with the approved terms and conditions2, 3
Credit Admin
4.05
Enrich any data (with appropriate controls e.g.. Audit Trail) that may not have been available at time of credit approval, w/o having to restart the process all over. Major changes will still require a fresh initiation e.g.. addition of new facilities.
New capability
Involves personal interaction
Existing capability enhanced

## Slide 18: Level 1 Process Maps – “To-Be” (5/ 11)
1 Activities may not occur in the numbered sequence. Activities can be performed in parallel and by different persons.
New capability
Existing capability enhanced
Involves personal interaction
VI. Facility Onboarding1
RM
CRM
Systems
Finacle (Loans), MLC/ Murex (Derivatives), TZ (FX), IMEX/ FactorPro (Trade), AOS, GCIN, CIS
6.03
Execute legal doc as per the PTS
6.04
Trigger CCU for activation and provide all supporting docs
6.02
Approve waivers, deferrals for conditions precedent with credit impact according to DOA
6.01
Check FA as per the approved credit terms conditions. Provide confirmation to RM
6.05
Auto CIF Creation for new borrower.
CCU/IBG Ops
6.06
Check compliance of CPs. Check limit structure and key credit data for STP to Finacle/C ASA/FCOD/TZ/
MLC for activation limit and enrich collateral data to STP to Finacle
6.08
STP covenants, upload insurance to Finacle
6.09
Digitized documents and update documents in imaging tool . Arrange for safe keeping.

## Slide 19: Level 1 Process Maps – “To-Be” (6/ 11)
1 Activities may not occur in the numbered sequence. Activities can be performed in parallel and by different persons.
New capability
Existing capability enhanced
Involves personal interaction
VII. Facility Utilization1
RM
Corp Loan Ops
CRM
Systems
Internal: OSCA, BBS, CIS, FRSP, Finacle (SG Loans), IPE, IDEAL, IWCC, ASIS, OnDemand, Oracle, GLAO system, Silverlight, QMS, TZ, CA, EOSA, SDEN
External: HPFLAS, MSIG GenLink, Spring Portal, Crown System
7.01
Submit requests for transaction deviations, excesses
7.02
Ad hoc trade highlights – Obtain blanket approval
7.03
To review request and either approve / reject request
7.04
Ensure Compliance with conditions pre-disbursement conditions for loans
7.06
Parallel processing with CCU - Auto Loan Creation by using upstream data
7.07
Parallel with CCU limit activation for Loan Disbursement, with upstream data. System perform check for limit activation prior to STP from Finacle to IPE./SAA (or other payment gateway)
CCU
7.08
Loan Servicing based on instructions received from workbench
7.09
Automated Reporting to internal/external parties and regulators.
7.05
Manual Uplift for ad-hoc transactions that failed auto uplift
Trade Ops
7.11
Automated population of customer specific credit conditions, pricing from upstream data systems to Trade Operating systems
7.12
Automated uplift notification to CCU, CRM and RM upon OT generation in Trade operating systems
7.13
Trade operating systems’ capability to trigger exception approvals at transaction level to IBG / CRM / BU for approval.

## Slide 20: Level 1 Process Maps – “To-Be” (7/ 11)
1 Activities may not occur in the numbered sequence. Activities can be performed in parallel and by different persons.
New capability
Existing capability enhanced
Involves personal interaction
RM
CRM
Systems
Finacle/E2E Credit Workbench
8.04
Perform periodic valuation of collateral (in accordance to guidelines), update system, escalate breaches
CCU
8.01
Prepare Group Review; interim + annual review (timely submission, satisfactory quality)
8.02
Monitor covenants
8.03
CCG to Approve Group Reviews + Risk Ratings
8.05
Check insurance renewal policy, highlight exceptions, update system.
8.06
Generate overdue covenants & Insurance, Sup Review, for escalation
8.07
R Cap – System capability to check that the limits allocated is within the approved R Cap limit
VIII. Risk Monitoring

## Slide 21: Level 1 Process Maps – “To-Be” (8/ 11)
1 Activities may not occur in the numbered sequence. Activities can be performed in parallel and by different persons.
New capability
Involves personal interaction
Existing capability enhanced
VIII. Risk Monitoring – Early Warning Triggers1
RM / CSO / CAT / ARM / BSU
Group SAM
CRM / Credit
Systems
Proposed e2e Credit Workbench / Reporting Platform
8.02
System to trigger borrowers based on predefined macroeconomic, quantitative and qualitative indicators, using data from both internal and external sources.
8.07
Generate reports e.g.. Watch List by Region, Migration etc for Management.
8.04
Based on severity of impact on borrowers., perform ACRR update, Credit Review and/or Watch List tagging (Amber, Red or Weak) where required.
8.05
Automated monitoring and tracking borrowers tagged as Watch List.
System to prompt and send email reminders of review deadlines.
8.06
Discuss with RM, review & approve :
ACRR update.
Credit Review.
Watch List Tagging.
Migration of Watch List borrowers.
Exemptions / deviations from Watch List.
8.09
Participate in review of borrowers tagged as Watch List - Weak at Review Meetings / Risk Exco / Board Exco.
8.08
Engage RM / CRM for clarification where required.
8.01
Discuss with CRM / SAM / RPU to establish Early Warning Triggers.
8.03
Review and apply judgmental overlay where required.

## Slide 22: Level 1 Process Maps – “To-Be” (9/ 11)
New capability
Involves personal interaction
Existing capability enhanced
VIII. Risk Monitoring – ICAAP / Ad hoc Stress
Relationship Manager
GPA
Credit Risk Manager
Systems
8.14
Review list of borrower –at-risk
8.15
Prepare portfolio-level NPL and SP projections
8.12
Create stress test models
Group Research / Country Risk
8.10
Prepare scenarios & macro-economic variables (MEV)
Finance
8.11
Provide Loan Growth Projections (ICAAP)
8.13
Apply models on MRA data to generate borrowers-at-risk with respective exposure
8.18
Generate EC & RWA Impacts (ICAAP)
8.16
Review borrower-specific remedial actions and prepare portfolio-level remedial actions
Stress Test Engine & Reporting Platform
8.14
Review list of borrower –at-risk & exposure reports
MLR
8.17
Simulate Stress Market Value
8.16
Prepare borrower-specific remedial actions

## Slide 23: Level 1 Process Maps – “To-Be” (10/ 11)
New capability
Involves personal interaction
Existing capability enhanced
VIII. Risk Monitoring – Portfolio Reporting
IBG Portfolio Owners
CRM
Systems
FRDM and Reporting Dashboard with Interactive, slice/dice functions
8.19
Group, Country and Industry Portfolio Reports generated monthly for IBG and Credit Portfolio Owners to manage and analyze their portfolio performance.
8.20
Group, Country and Industry Portfolio Reports generated monthly for IBG and Credit Portfolio Owners with drill down capability for Portfolio owners to manage and analyze their portfolio.
8.21
Daily Client Dashboard for RM and CRMs to manage and analyze their clients portfolio.
RM
Credit Portfolio Owners
8.22
Customizable Portfolio and Client Dashboard for Portfolio owners, RM and CRMs to manage and analyze their portfolio. Portfolio owners, RM and CRMs have the ability to set threshold, alerts and limits.
Internal Reporting Team
8.23
Dashboard that allows Reporting team to slice and dice or self create ad hoc reports.

## Slide 24: Level 1 Process Maps – “To-Be” (11/ 11)
Existing capability enhanced
New capability
Involves personal interaction
IX. Remediation
9.02
Definition of Default
Technical or Subjective default
9.01
Watchlist and Weak Credit Process
- Auto tagging and auto notification upon quantitative triggers
9.08
System Update
- Automate system to reflect both GL account and actual liabilities owing by NPL borrowers
9.05
Monthly Specific Provision Forecasting Process
9.09
Post Mortem Review
GROUP SAM
Systems
Proposed e2e Credit Workbench
9.07
Write-off and Write-back process
Include STP to PSGL (auto post of GLs) and loan booking system
9.06
Restructuring / Recovery Process
9.03
Determination of NPA and transfer of account from IBG to Group SAM
- Auto downgrade to NPL upon dpd exceeding 90 days trigger
9.04
Monthly NPA and Specific Provision Review
Include STP to PSGL (auto posting of GLs)